## Summary
SEA Service Portal – Summary
Counts update from the Requirements sheet.
Service area | Exists | Partial | Gap | Total | Must | Done
Common Portal | 4 | 6 | 8 | 18 | 15 | 0
IT Services | 2 | 4 | 1 | 7 | 4 | 0
Facilities | 0 | 2 | 2 | 4 | 3 | 0
Student Services | 0 | 0 | 3 | 3 | 2 | 0
Translation Service | 1 | 0 | 3 | 4 | 3 | 0
Academic Team | 0 | 2 | 2 | 4 | 2 | 0
Service Levels | 0 | 2 | 1 | 3 | 2 | 0
Total | 7 | 16 | 20 | 43 | 31 | 0
Key
Exists | Already built in SEA IT Service Desk; reuse
Partial | Built for agents; needs an end-user version
Gap | New build

## Requirements
SEA Service Portal – End-User Requirements mapped to SEA IT Service Desk
Mapped to the SEA IT Service Desk artifact (Incidents, Requests, Changes, Assets, Admin console). 'In current system': Exists = already built and reused; Partial = built for agents, needs a portal/end-user version; Gap = new build. Priority, Status, Owner and Notes are editable (yellow). Priorities are proposals to confirm with each department.
Req ID | Service area | Maps to module | Requirement | In current system | Current behaviour | What to build | Permission key | Priority | Status | Owner | Notes
COM-01 | Common Portal | New: Portal (#portal) | Separate end-user portal view inside the same page, opened by default for users without an agent role | Gap | Users without a role see the 'Request access' gate only | Add a Portal route and a 'Requester' role so every SEA user lands on the portal, not the agent workspace | port.view | Must | Not started
COM-02 | Common Portal | Admin console › Users & access | Sign in with academy identity; name, email and avatar picked up automatically | Exists | Uses the signed-in Claude identity (user capability, profile scope) | Auto-grant the Requester role to all SEA users instead of manual access approval | adm.users | Must | Not started
COM-03 | Common Portal | Portal | Arabic and English interface with right-to-left layout, switchable per user | Gap | English only; dates formatted en-GB | Add language toggle (remember per viewer), RTL stylesheet, bilingual labels for catalogue, statuses and notifications | — | Must | Not started
COM-04 | Common Portal | Portal › Home | Home page with search, five service-area tiles (IT, Facilities, Student Services, Translation, Academic), announcements and 'My open requests' | Gap | Overview page is agent KPIs only | Build portal home reusing panel, kpi and row components | port.view | Must | Not started
COM-05 | Common Portal | Portal › Search | One search across catalogue items, help articles and the user's own tickets | Partial | Search box filters ID, title, requester inside each agent list | Extend search to catalogue and knowledge for end users | port.view | Must | Not started
COM-06 | Common Portal | Portal › Assistant | Claude assistant that answers questions, suggests the right catalogue item and pre-fills the form | Gap | None | Use the page's 'ask Claude' runtime capability; user confirms before submit | port.create | Must | Not started
COM-07 | Common Portal | Requests (REQ) | Department-based service catalogue covering all five service areas | Partial | CATALOG has 8 IT items only; DEPT list holds requester departments, not service areas | Add a 'serviceArea' field and a catalogue per area (see Catalogue Mapping sheet) | req.create | Must | Not started
COM-08 | Common Portal | New ticket form | Dynamic request forms per catalogue item: conditional fields, mandatory checks, attachments | Partial | One fixed form per ticket kind (title, item, approver, requester, department, details); no attachments | Form definition per catalogue item stored in settings; add file upload (files capability) | req.create | Must | Not started
COM-09 | Common Portal | New ticket form | Requester filled automatically from the signed-in user; option to raise on behalf of someone else | Partial | Requester is typed free text | Default requester = ME; 'On behalf of' people picker reusing the Admin user picker | req.create | Should | Not started
COM-10 | Common Portal | Portal › My requests | 'My requests' list: ID, status pill, assigned team, SLA due date, last update | Gap | Agents see all tickets; no requester filter | List tickets where requesterId = ME, using existing table, pill() and sla() | port.view | Must | Not started
COM-11 | Common Portal | Ticket drawer | Requester view of a ticket: timeline of public updates, add comment and attachment, cancel, reopen within 5 days | Partial | Drawer shows activity log with internal work notes only | Split activity into public replies vs internal work notes; requester actions Cancel / Reopen | port.update | Must | Not started
COM-12 | Common Portal | Notifications | Email, Teams and mobile notifications on submit, status change, approval needed, resolved | Gap | Toast messages inside the page only | Add notifications; respect user preferences | — | Must | Not started
COM-13 | Common Portal | Requests › Approval box | Approvers approve or reject from the portal (and later from email/mobile) | Partial | Agent clicks 'Record approval / rejection' on the approver's behalf (req.approve) | Route approval to the named approver user; approver acts directly in the portal | req.approve | Must | Not started
COM-14 | Common Portal | Ticket drawer | Satisfaction rating (1–5 + comment) when a ticket is Resolved / Completed | Gap | None | Prompt requester on DONE statuses; store csat on ticket; show on Overview | port.update | Must | Not started
COM-15 | Common Portal | New: Knowledge | Help articles and FAQs per service area, bilingual | Gap | None | New Knowledge module with kb.view / kb.create permissions | kb.view | Should | Not started
COM-16 | Common Portal | Layout | Mobile-friendly portal | Exists | Responsive layout at 900 px and 520 px breakpoints already in place | Keep the same breakpoints for portal views | — | Must | Not started
COM-17 | Common Portal | Admin console › Branding | Portal uses SEA name, short mark and brand colour | Exists | Branding tab: institution name, short mark, colour presets, theme | Apply the same BRAND settings to the portal | adm.branding | Must | Not started
COM-18 | Common Portal | Admin console › Audit log | All portal submissions, approvals and status changes logged | Exists | audit/ entries written for admin actions | Also write audit entries for portal actions | adm.audit | Should | Not started
IT-01 | IT Services | Incidents (INC) | 'Report a problem' in the portal creates an INC ticket | Partial | Agents log INC with category, impact, urgency, CI | Simplified portal form: what's wrong, category, location, how urgent; agent sets impact | inc.create | Must | Not started
IT-02 | IT Services | Incidents (INC) | Incident categories shown to users | Exists | INC_CAT: Network & Wi-Fi, Hardware, Classroom AV, Email & Accounts, Software, Printing, LMS | Confirm against IT's already-defined categories and align the list | — | Must | Not started
IT-03 | IT Services | Requests (REQ) | 'Request a service' in the portal creates a REQ ticket from the IT catalogue | Partial | CATALOG: New laptop, Software installation, Account access, Classroom AV setup, Shared drive access, Printer toner / repair, Guest Wi-Fi for event, Phone extension | Replace or extend with IT's defined service categories | req.create | Must | Not started
IT-04 | IT Services | Incidents (INC) | Priority from impact × urgency, with SLA shown to the user | Exists | prioM(): P1 4h, P2 8h, P3 24h, P4 72h resolution | Show expected resolution time on the user's ticket | — | Must | Not started
IT-05 | IT Services | Assets | Pick the affected device from the user's own assets | Partial | Asset register with assignedTo as free text; CI picker on agent form | Link assets to user IDs; show 'My devices' in the portal | ast.view | Could | Not started
IT-06 | IT Services | Changes (CHG) | Service status banner for outages and planned maintenance | Partial | Change schedule shown to agents on Overview | Publish Scheduled / Implementing changes and open P1s as a portal status banner | port.view | Should | Not started
IT-07 | IT Services | Portal | Self-service password reset, MFA reset and account unlock | Gap | None | Needs identity-system integration; until then raise as 'Account access' REQ | — | Should | Not started
FAC-01 | Facilities | Requests (REQ) + Incidents (INC) | Facilities catalogue: maintenance fault, room/lab booking, access card, parking/transport, housekeeping and event setup | Gap | Facilities is only a requester department and an asset owner | Add serviceArea = Facilities with its own catalogue and assignment group | req.create | Must | Not started
FAC-02 | Facilities | New ticket form | Maintenance form with building, room and photo | Partial | LOC list exists: Main Building, Training Block A, Training Block B, Library, Admin Wing, Auditorium, Data Room | Reuse LOC; add room number and photo upload | req.create | Must | Not started
FAC-03 | Facilities | Incidents (INC) | Urgent / safety flag that maps to P1 handling | Partial | Impact × urgency matrix exists | Safety flag sets High / High = P1 and alerts the Facilities team | inc.create | Must | Not started
FAC-04 | Facilities | New: Bookings | Room, lab and event space booking with availability calendar | Gap | None | Booking module; Auditorium and AV setup link to IT 'Classroom AV setup' | — | Should | Not started
STU-01 | Student Services | Requests (REQ) | Student Services catalogue: letters and certificates, transcripts, enrolment / registration / fee queries, ID card, complaints and enquiries | Gap | None | Add serviceArea = Student Services, catalogue and team | req.create | Must | Not started
STU-02 | Student Services | Roles | Students / trainees can use the portal | Gap | Roles are staff/agent roles only | Requester role covers students; restrict them to their own tickets | port.view | Must | Not started
STU-03 | Student Services | Ticket drawer | Download link when a letter or document is ready | Gap | No attachments | Agent attaches the document on Completed; requester downloads it | port.view | Should | Not started
TRN-01 | Translation Service | Requests (REQ) | Translation request from the already-defined translation form | Gap | None | Digitise the existing form field-for-field as one catalogue item | req.create | Must | Not started
TRN-02 | Translation Service | New ticket form | Upload source document; language pair, document type, deadline | Gap | No attachments, no date field on REQ | Add file upload and 'Required by' date | req.create | Must | Not started
TRN-03 | Translation Service | Requests › Approval box | Approval step if the current process requires one | Exists | Submitted → Awaiting Approval → Approved / Rejected flow | Reuse as is; set approver per catalogue item | req.approve | Should | Not started
TRN-04 | Translation Service | Ticket drawer | Download translated file; request a revision | Gap | None | Attachment on Completed; 'Request revision' reopens to Fulfilling | port.update | Must | Not started
ACA-01 | Academic Team | Requests (REQ) | Academic request from the already-defined academic form | Gap | None | Digitise the existing form field-for-field as one catalogue item | req.create | Must | Not started
ACA-02 | Academic Team | Requests (REQ) | Route to the correct academic unit / programme automatically | Partial | DEPT list includes Teacher Training, Leadership Programmes, Research | Assignment rule by programme field | req.update | Should | Not started
ACA-03 | Academic Team | Requests › Approval box | Multi-level approval (e.g. programme lead, then dean) | Partial | Single approver per request | Allow an ordered list of approvers | req.approve | Should | Not started
ACA-04 | Academic Team | New ticket form | Attach supporting documents | Gap | No attachments | File upload (shared with other areas) | req.create | Must | Not started
SLA-01 | Service Levels | SLA engine | Expected response and completion time shown on each catalogue item and ticket | Partial | SLA_INC P1–P4 and SLA_REQ 72h; sla() returns Met / Breached / time left | Make SLA configurable per service area and catalogue item; show due date to requester | — | Must | Not started
SLA-02 | Service Levels | Overview › Needs attention | Reminder and escalation when a ticket is overdue | Partial | Agents see breached / at-risk (under 25% left) list | Send reminder at 75% and escalate to team lead on breach | — | Must | Not started
SLA-03 | Service Levels | SLA engine | Business hours and UAE public holidays in SLA calculation | Gap | SLA counts 24/7 clock hours | Add working calendar to sla() | — | Should | Not started

## Catalogue Mapping
Service catalogue mapped to SEA IT Service Desk ticket kinds
Each catalogue item becomes an INC (problem) or REQ (service) ticket with a new 'serviceArea' field, so the existing lists, SLA and approval flow are reused. IT items come from the system's current INC_CAT and CATALOG lists.
Service area | Catalogue item | Ticket kind | ID prefix | In current system | Approval needed | Approver | SLA target | Portal form fields | Notes
IT | Report a problem (Network & Wi-Fi, Hardware, Classroom AV, Email & Accounts, Software, Printing, LMS) | INC | INC- | Exists (INC_CAT) | No | — | Impact × urgency: P1 4h · P2 8h · P3 24h · P4 72h | What's wrong, category, location, device (optional), how urgent, details | Confirm against IT's defined categories
IT | New laptop | REQ | REQ- | Exists (CATALOG) | Yes | Line manager | 72h | Who for, start date, keyboard (Arabic/English), accessories
IT | Software installation | REQ | REQ- | Exists (CATALOG) | Yes | Line manager | 72h | Software name, licence source, device
IT | Account access | REQ | REQ- | Exists (CATALOG) | Yes | Line manager | 72h | System, access level, reason
IT | Classroom AV setup | REQ | REQ- | Exists (CATALOG) | No | — | 72h | Room, date/time, equipment needed
IT | Shared drive access | REQ | REQ- | Exists (CATALOG) | Yes | Folder owner | 72h | Folder path, read or read/write
IT | Printer toner / repair | REQ | REQ- | Exists (CATALOG) | No | — | 72h | Printer tag, location, issue
IT | Guest Wi-Fi for event | REQ | REQ- | Exists (CATALOG) | No | — | 72h | Event name, dates, number of guests
IT | Phone extension | REQ | REQ- | Exists (CATALOG) | Yes | Line manager | 72h | User, location, extension type
Facilities | Maintenance fault | INC | INC- | New | No | — | Same P1–P4 matrix; safety flag = P1 | Building (LOC), room, issue type, photo, safety flag
Facilities | Room / lab booking | REQ | REQ- | New | Optional | Facilities coordinator | To confirm | Space, date, start/end time, attendees, setup
Facilities | Access card | REQ | REQ- | New | Yes | Line manager | To confirm | Card holder, areas needed, start date
Facilities | Parking / transport | REQ | REQ- | New | Yes | Line manager | To confirm | Type, dates, pickup/drop-off
Facilities | Housekeeping / event setup | REQ | REQ- | New | No | — | To confirm | Location, date/time, requirements
Student Services | Letter / certificate | REQ | REQ- | New | No | — | To confirm | Letter type, addressed to, language (AR/EN), delivery method
Student Services | Transcript / document | REQ | REQ- | New | No | — | To confirm | Document type, copies, language
Student Services | Enrolment / registration / fee query | REQ | REQ- | New | No | — | To confirm | Programme, query type, details
Student Services | ID card issue / replacement | REQ | REQ- | New | No | — | To confirm | Reason, photo upload
Student Services | Complaint / general enquiry | REQ | REQ- | New | No | — | To confirm | Topic, details, attachment
Translation | Translation request | REQ | REQ- | New (form already defined) | Per current process | Per current process | To confirm | Use the existing translation form fields as they are | Share the form to map fields one-to-one
Academic Team | Academic request | REQ | REQ- | New (form already defined) | Per current process | Programme lead → Dean (if needed) | To confirm | Use the existing academic form fields as they are | Share the form to map fields one-to-one

## Statuses & SLA
Ticket statuses and SLA from SEA IT Service Desk
Statuses are the system's FLOW lists. The portal shows friendlier labels to end users (column C).
Ticket kind | Agent statuses (current) | Portal label for end users | Closed statuses | Requester actions
Incident (INC) | New → In Progress → On Hold → Resolved → Closed | Logged / Being worked on / Waiting / Fixed – please confirm / Closed | Resolved, Closed | Requester can reopen within 5 days of Resolved (new)
Request (REQ) | Submitted → Awaiting Approval → Approved → Fulfilling → Completed / Rejected | Submitted / Waiting for approval / Approved / In progress / Done / Not approved | Completed, Rejected | Requester can cancel before Fulfilling (new)
Change (CHG) | Draft → Assessment → CAB Review → Scheduled → Implementing → Completed / Cancelled | Shown only as planned maintenance on the status banner | Completed, Cancelled | Agents only
SLA targets (current system)
Priority / type | Target | Applies to
P1 (High impact, High urgency) | 4 hours | Incident resolution
P2 | 8 hours | Incident resolution
P3 | 24 hours | Incident resolution
P4 | 72 hours | Incident resolution
All requests | 72 hours | Request fulfilment
At-risk warning | Under 25% of SLA left | Shown amber on Overview

## Roles & Permissions
Roles: existing in SEA IT Service Desk + new for the portal
Existing roles come from DEFAULT_ROLES in the system. New roles and permission keys (port.*, kb.*, area scoping) are needed for end users and the four new departments.
Role | Existing / New | Purpose | Permissions | Page sharing needed
Administrator | Existing | Full control, including users, roles and branding | All | Editor
Service Desk Manager | Existing | Runs the desk across all modules; audit log | All except adm.users, adm.roles, adm.branding | Contributor
Agent | Existing | Handles incidents and requests | *.view, inc.create/update/assign, req.create/update, chg.create, ast.update | Contributor
Change Approver (CAB) | Existing | Reviews and approves changes | *.view, chg.update, chg.approve | Contributor
Asset Manager | Existing | Keeps the asset register accurate | *.view, inc.create, ast.create, ast.update | Contributor
Read-only | Existing | Sees everything, changes nothing | *.view | Viewer
Requester (all staff, faculty, students) | New | Uses the portal: raises and tracks own tickets | port.view, port.create, port.update (own tickets only), kb.view | Contributor
Department Approver | New | Approves requests routed to them in the portal | port.*, req.approve (assigned to them) | Contributor
Department Agent (Facilities, Student Services, Translation, Academic) | New | Works tickets for one service area only | inc/req view, update, assign scoped to serviceArea | Contributor
Knowledge Editor | New | Writes and publishes help articles | kb.view, kb.create, kb.update | Contributor

## Ticket Data Model
Ticket fields: current schema + additions for the portal
Current fields come from the tickets collection in the SEA IT Service Desk. New fields let the same ticket record serve all five service areas.
Field | Existing / New | Meaning | Change for portal
id | Existing | INC-2041 / REQ-1188 / CHG-311 | Keep
kind | Existing | INC, REQ, CHG | Keep
title, desc | Existing | Short description and details | Keep
status | Existing | From FLOW per kind | Keep; add portal labels
priority, impact, urgency | Existing | INC only, P1–P4 | Keep
category / item | Existing | INC category or REQ catalogue item | Keep; values per service area
requester | Existing | Free text name | Change to requesterId (signed-in user) + name
dept | Existing | Requester's department | Keep
assignee | Existing | Agent user ID | Keep
approver | Existing | Free text | Change to approver user ID(s), ordered list
asset | Existing | Configuration item tag | Keep
activity[] | Existing | {who, text, at} | Add 'public' flag to split replies from work notes
created, updated, closedAt | Existing | Timestamps | Keep
serviceArea | New | IT, Facilities, Student Services, Translation, Academic | Drives catalogue, team queue and SLA
formData | New | Answers to the catalogue item's form fields | Stored as key/value
attachments[] | New | Uploaded files (source docs, photos, outputs) | Needs files capability
requiredBy | New | Deadline the requester needs | Translation, bookings
onBehalfOf | New | User the request is for | Optional
csat | New | {score 1–5, comment, at} | Captured on Resolved / Completed
lang | New | ar / en | Language for notifications